## Sheet1
Week commencing date
Activity | Task Owner | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09
Contact team | All
Choose applications/tools | All
Write Group Project Plan | All
Research literature | Mark
Data exploration + prep | Hao
Modelling | Louis
Produce visualisation + outputs | Charlet
Create report | Louis + Hao
Create presentation | Mark
Rehease | All
Group video presentation | All